Sample Timeline

- Always start a timeline from the date of the event and work backwards.

- Schedule all meetings of the program team.

- With the help of the checklist, schedule tasks and deadline dates.

EVENT: End of the Year Awards Ceremony/Banquet

EVENT DATE: Saturday, May 1, 2010

TIME: 6:00 pm	PLACE: Ballrooms ABC - University Student Union

DATE:	TASK/ASSIGNMENT:

5/1/10   	Awards Ceremony/Banquet

4/28/10            Final meeting of the Awards Program Planning Team to tie up loose ends

4/24/10     	Meet with campus officials to confirm tasks and complete last minute trouble shooting.

4/15/10	Awards Program Planning Team: reports on task assignments from member.

4/1/10	Have SLD Advisor sign off for final approval on PRC and submit to the USU Conference and Events Center

3/15/10	Slide show prepared. Awards Program Planning Team: reports on task assignments from members, review and update budget.

3/3/10		Flyers created and posted.  Press releases submitted.

3/1/10		Invitations mailed. Decorations ordered.

2/28/10	Disk Jockey contracted

2/25/10            Food and refreshments ordered/contracted

2/20/10	Invitation selected and ordered

2/15/10	Equipment ordered.  Awards Program Planning Team: reports on task assignments from members, review and update budget.

2/10/10	Guest list finalized

2/1/10	First meeting of Awards Program Planning Team for the semester.  Program Checklist developed: assignment of tasks to members of the team

11/20/10          See SLD Advisor for PRC and schedule event at the USU Conference and Events 	Center

11/15/10          Student Organization meeting to brainstorm awards program ideas and select the date, 			determine the chair and members of the Awards Program Planning team.  Budget 				designated.

POST EVENT TIMELINE:

5/3/10  	Awards Program Planning Team meets to evaluate the program

5/10/10	Program manual complied for next year’s team

5/11/10	Thank you notes written and sent.